## FLAContact
flaconMemberState | flarepCode | flaconReportedPeriod | flaconVersion | flaconSituationAt | flaconName | flaconInstitution | flaconStreet | flaconZIP | flaconCity | flaconPhone | flaconFax | flaconEmail | flaconRemarks
Finland | FI2020ART17 | 2020 | 2022-06-20 | 2020-12-31 | Mr Jonne Sayla | Finnish Environment Institute | Latokartanonkaari 11 | FI-00790 | HELSINKI | +358 295 251 667 |  | jonne.sayla@syke.fi

## FLAAgglomerations
flarepCode | aggCode | aggName | flaggStatus | flaggReasons | flaggMeasures | flaggExpecDateStart | flaggExpecDateStartWork | flaggExpecDateCompletion | flaggInv | flaggEUFundName | flaggEUFund | flaggComments | flaggExpLoad | flaggExpLoadColl | flaggExpLoadIAS | flaggOtherFund | flaggOtherFundName | flaggLoan | flaggLoanName

## FLAUWWTPs
flarepCode | uwwCode | uwwName | flatpStatus | flatpReasons | flatpMeasures | flatpExpLoad | flatpExpCapacity | flatpExpecTreatment | flatpExpecDateStart | flatpExpecDateStartWork | flatpExpecDateCompletion | flatpExpecDatePerformance | flatpInv | flatpEUFundName | flatpEUFund | flatpComments | flatpExpLoadTruck | flatpOtherFund | flatpOtherFundName | flatpLoan | flatpLoanName
FI2020ART17 | FIJVP_O000000000089 | TP (89) of Heinolan kt. | NC | Insufficient N removal / TP under renovation that has caused operational disturbancies | Renovation has been successful and the new process has been started with external carbon source | 21200 | 23000 | 3NP | 2018-01-01 | 2018-12-31 | 2021-12-31 | 2023-01-01 | 8
FI2020ART17 | FIJVP_O001300000055 | TP (1300000055) of akaslompolo | NC | Insufficient BOD, COD and TSS removal / TP at the end of it's operational life | New TP has been constructed and completed | 12000 | 21500 | 3NP | 2019-01-01 | 2020-01-01 | 2021-09-30 | 2022-12-31 | 8
FI2020ART17 | FIJVP_O000000000525 | TP (525) of Mantsalan kk. | NC | Insufficient N removal / insufficient carbon source for proper denitrification | Up-date of process automation and preparation for process renovation | 14400 | 13600 | 3NP | 2022-01-01 | 2022-12-31 | 2024-12-31 | 2025-12-31 | 4
FI2020ART17 | FIJVP_O000000000218 | TP (218) of Kankaanpaan kt. | NC | Insufficient N removal / insufficient carbon source for proper denitrification | Enhanced activated sludge process configuration for better denitrification | 15500 | 12500 | 3NP | 2022-01-01 | 2023-04-30 | 2023-12-31 | 2024-12-31 | 0.4

## FLAInvestments
flarepCode | soecCode | soecStartYear | soecEndYear | soecPeriod | soecCapacity | soecInvCol | soecInvTp | soecInvComments | soecInvIAS | soecOpCosts | soecEUFunds | soecJobs | soecLenghtCoCs | soecLenghtSaCs | soecLenghtStCs | soecNumbIAS | soecPop
FI2020ART17 | FIUWWINV2018 | 2018-01-01 | 2018-12-31 | P | 6900000 | 325 | 55 |  |  | 279 | [6 empty] | 5520000
FI2020ART17 | FIUWWINV2019 | 2019-01-01 | 2019-12-31 | P | 7000000 | 329 | 55 |  |  | 279 | [6 empty] | 5525000
FI2020ART17 | FIUWWINV2020 | 2020-01-01 | 2020-12-31 | P | 7100000 | 334 | 55 |  |  | 279 | [6 empty] | 5534000
FI2020ART17 | FIUWWINV2021 | 2021-01-01 | 2021-12-31 | P | 7200000 | 338 | 55 |  |  | 279 | [6 empty] | 5548000
FI2020ART17 | FIUWWINV2022 | 2022-01-01 | 2022-12-31 | CU | 7300000 | 343 | 55 |  |  | 290 | [6 empty] | 5550000
FI2020ART17 | FIUWWINV2023 | 2023-01-01 | 2023-12-31 | EXP | 7300000 | 349 | 55 |  |  | 310 | [6 empty] | 5550000
FI2020ART17 | FIUWWINV2024 | 2024-01-01 | 2024-12-31 | EXP | 7300000 | 356 | 55 |  |  | 330 | [6 empty] | 5550000
FI2020ART17 | FIUWWINV2025 | 2025-01-01 | 2025-12-31 | EXP | 7300000 | 363 | 55 |  |  | 350 | [6 empty] | 5550000
FI2020ART17 | FIUWWINV2026 | 2026-01-01 | 2026-12-31 | EXP | 7300000 | 370 | 55 |  |  | 370 | [6 empty] | 5550000

## DO_NOT_DELETE_THIS_SHEET
Please do not delete or modify this sheet!!!
It is used for converting this file back to XML!
Without this possibility your work cannot be used!
http://dd.eionet.europa.eu/v2/dataset/3463/schema-dst-3463.xsd
TableID | SchemaURL
FLAContact | http://dd.eionet.europa.eu/v2/dataset/3463/schema-tbl-11643.xsd
FLAAgglomerations | http://dd.eionet.europa.eu/v2/dataset/3463/schema-tbl-11641.xsd
FLAUWWTPs | http://dd.eionet.europa.eu/v2/dataset/3463/schema-tbl-11642.xsd
FLAInvestments | http://dd.eionet.europa.eu/v2/dataset/3463/schema-tbl-11644.xsd